Adopted Minutes for Website Committee Conference Call

Tuesday August 9, 2005, 11:00 AM

Attendees:

Tim Caulfield – Equipoise

Pierre Landry – SCE

Beatrice Mayo – PG&E

Peter Lai – CPUC

Sylvia Bender – CEC

Absent

Bill Junker – CEC

Peter Puglia– CEC

Mary Wold – SDG&E

##### Executive Summary

The CALMAC Website Committee held its rescheduled August conference call to address the items shown in the attached agenda. Mostly the call covered (1) discussion of the three status reports that have been updated during the past month, and (2) discussion about finding existing Nontechnical Overviews and creation of same for new contracts. The regular September call will not be held and the next conference call is scheduled for Tuesday, October 11th at 11:00 AM.

Minutes of Conference Call (in order of agenda) Call started ~11:10 AM

- Approve minutes of July 14 Website Committee conference call. No comments. Adopted.

- MAESTRO Project Quarterly Status Report – The end of second quarter report is now available on the website. Feedback is appreciated. The announcement was sent out to the list serve for the first time as agreed previously.

- Nontechnical Overviews – At Itron, Jennifer Holm, who has now taken responsibility for these and she promised to call me back no matter what happens. Haven’t heard from her yet. Tim Caulfield will send a note to Rich Pullium requesting any Nontechnical Overviews that he has in his files.

- Website Committee quarterly report to CALMAC is attached below. It will be presented at the September 21st CALMAC meeting since the August meeting has been canceled. Feedback is appreciated. Use of site continues to creep upward.

- Status of third party report submission to site. Equipoise has updated the third party submission report. The percentage of available reports on the site has slipped from about 65% to 53%. This is because more reports have become available, and they need to be posted to the site. Peter Lai plans to send out a broad email to all third parties thanking those that have posted the reports and requesting those who have not to post them.

- Any other important issues about the site?

- Equipoise plans to check site to be sure that information on the site is up to date over the next couple of months.

- 2-4 Page Summaries (also called Nontechnical Overviews) – Are all of the utilities doing them for all contracts? Comments: Those that have them in the contract we will post them. Can we add this to the status report as to whether 2-4 pagers are going to be done on the project? This would allow follow up later to know whether they should be posted. This would be a lot of work, do we really want to do this. Agreement: If they are in the contract, it will be done and posted by PMs, if it isn’t in the contract it will not be done (or will be posted if contractor does on own), we will try to get it in all future contracts.

- Adjourn conference call: 11:45 AM. By unanimous agreement the call on Tuesday, September 13th will be skipped and the next call will be at 11:00 AM October 11th.

Draft Agenda for Website Committee Conference Call

11:00 AM, Tuesday, August 9, 2005

Dial in Number: 1-888-900-1820

Participant Passcode: 578021

- Approve minutes of July 14 Website Committee conference call. (Minutes available in the Website area at the bottom of the Administration page of CALMAC.org. Direct link to this page is

http://www.calmac.org/website-agendas.asp

- MAESTRO Project Quarterly Status Report – The end of second quarter report should be available on the website prior to our call. Feedback is appreciated.

- Nontechnical Overviews –At Itron, Jennifer Holm, who has now taken responsibility for these and she promised to call me back no matter what happens.

- Website Committee quarterly report to CALMAC is attached below. It will be presented at the September 21st CALMAC meeting since the August meeting has been canceled. Feedback is appreciated.

- Status of third party report submission to site. Equipoise has update the third party submission report. It will be discussed on call.

- Any other important issues about the site?

- Adjourn conference call. Next call: Tuesday, September 8th at 11:00 AM.

CALMAC Website Committee Status Report

to

CALMAC Meeting – 7/20/05

The following is a report of the status of the key Website efforts as of July 20, 2005.

Site Statistics – The following are the key statistics on the CALMAC website:

- Hits – Website usage can be summarized as follows:

  - Between June ’04 and June ’05 the website has averaged approximately 18,000 page request per month, with a total of 216,468 page requests for the 12 months period. This is up approximately 31% from the same period a year earlier.

  - Overall the number of page requests has risen steadily since August of 2002.

### CALMAC.org Page Requests per Month, August 2002 through June 2005

  - The most common hours for visits remain between 8 AM for 5PM PST during weekdays. This continues to suggest that the primary users are California based organizations.

The figures above represent the sum of all page requests from March 11th 2004 to July 16th , 2005.

- Searchable database  - As of 7/20/05 the CALMAC Searchable Database

  - Contains 722 records representing 606 unique reports.

  - The reports cover programs from 1990 to present and approximately sixty nine percent (69%) of these reports have downloadable electronic files. The average file size is 1,928 kilobytes and the median files size is 679 kilobytes. This says that there are some very large files, but that the majority (60%) are less than 1,000 kilobytes (1 megabyte).All of the records without electronic files are either pre-1996 or are appendices to reports that do have electronic files.

  - 12 unique reports have been submitted in the past three months.

  - The reports in the database now cover 35 different implementers, of which 25 are third party implementers. Twenty-five (25) unique third party reports are now in the database. Peter Lai of the CPUC staff is continuing his efforts to get third parties to submit reports. An assessment for him completed in July 2005 indicated that 53% of the available the third party programs reports had been submitted to CALMAC.org

  - During 2004 visitors requested 107,505 Adobe Acrobat Portable Document File (PDF) documents (~8,960 per month). During the 6 month period from January 1, 2005 to June 30, 2005 there have been 66,085 PDF files requested, (11,014/month, 499/work day, ~62/ working hour, ~1/ work minute), representing about a 31% increase over the same period in 2004. Since the vast majority of PDF documents on the site are in the searchable database, this gives a very good indication of the number of reports requested from the searchable database.

MAESTRO Project Quarterly Status Report - Status

An updated version of the MAESTRO Project Status Quarterly Report will be posted (CALMAC/MAESTRO/Quarterly Reports) in August 2005, covering the status as of the end of the second quarter of 2005. The report will continue to be updated quarterly in both Microsoft Word and Excel versions. The availability of this report will be announced using the CALMAC list serve. Similar announcements will be made each time an updated report is posted.

Report Posting

Due to temporary staff unavailability at the CEC, Equipoise took over responsibility for posting and announcing availability of reports starting in early November 2004, and has continued to fill this need since then. Recent discussions with CEC staff have made this change permanent. The CEC will continue to be the librarian for paper copies or the reports.

Website Committee Reports to CALMAC

The CALMAC Website Committee has decided, unless CALMAC objects, to decrease the frequency of reports to CALMAC to twice per year. This is being done because the CALMAC website is now fairly well established, thus requiring less frequent reporting, and to decrease the cost of reporting (each report taking approximately 3 hours to prepare).

Project to date Spent/Spending Status

The website project started in May of 2002 with the purpose of upgrading the website. The following table includes a summary of all spending to date for the website project, exclusive of CEC costs. CEC staff have historically performed the library function for the database, entering and announcing reports and distributing hard copies on request.

# Spending to July 1, 2005 on Website/Database

| Description | Budget | Spent to Date |
| --- | --- | --- |
| Phase 1 – Initial re-arrangement of site and SoW development for Database Rehab. (Complete) | $25,000 | $25,000 |
| Phase 2 – Collection of all evaluation reports for programs post 1/1/94, creation of electronic files, creation of database structure, testing and launching site and database, continued development of site. Hosting of site. (Complete) | $85,000 | $85,000 |
| Phase 3 – Site maintenance and operation. Upgrading of site content, completion of policy manual and site documentation, promotion of site, training of user. Hosting of site. | $50,000 | $50,000 |
| Phase 4 – Site maintenance and operation. Upgrading reporting capabilities and support of CPUC and CALMC site needs. | $140,000 | $16,569 |
| Total | $300,000 | $176,569.00 |

July 27, 2005

To: 	Peter Lai, California Public Utilities Commission

From:	Tim Caulfield, Equipoise Consulting Incorporated

Cc: 	Cynthia  Rogers, California Energy Commission
	Mary Sutter, Equipoise Consulting Incorporated

Re:	Status of 2002-2003 Program EM&V Reports Posted to CALMAC.org

This memorandum summarizes an analysis of the 2002-2003 energy efficiency programs EM&V report filing status. The primary purpose of the analysis was to figure out whether the available EM&V reports are posted to CALMAC.org searchable database.

Exhibits 1 and 2 show that as of July 27, 2005, forty-seven (47) EM&V reports have been filed with the CPUC. Of these 47, Exhibit 1 shows that 25 (53%) have been posted to the CALMAC.org searchable database. Exhibit 3 shows that an additional 14 programs have not yet filed EM&V reports.

Exhibit 2 supplies the current list of programs that should be contacted to encourage them to post their EM&V study reports to CALMAC.org.

For your convenience I have included, after Exhibit 3, a summary of how one goes about posting a report to CALMAC.org.

If you have any questions please call me at any time. Since some of my contact information has changed recently it is repeated below.

Tim Caulfield

2415 Roosevelt Drive

Alameda CA 94501

510-414-0056

Fax 510-864-8507

Tim@EquipoiseConsulting.com

Exhibit 1

2002-2003 Programs with EM&V  with Studies Completed and Reports Posted to CALMAC.org Searchable Database

Exhibit 2

2002-2003 Programs with EM&V Studies Completed but Not Posted to CALMAC.org Searchable Database

Exhibit 3

2002-2003 Programs Where EM&V Study has Yet to be Completed

Submitting Your Report to CALMAC.org

Your evaluation report can be easily submitted to the CALMAC.org website over the Internet.

- If you don’t already have a CALMAC Study ID for the report, send an email to Tim@EquipoiseConsulting.com supplying the name of the implementer and the full title of the report. You will get a CALMAC Study ID by return email.

- Go to www.CALMAC.org, select the Administration page from the menu on the left, and then select the hotlink in the first bullet in middle of the page titled Reports to be Posted to our Searchable Database. This will bring up the form for submitting a report.

- Fill out the form and attach the file.  Note: If you want detailed instructions on how to submit the report or if you find the instructions on the form unclear about what to put in a particular box, simply return to the Administration page and select the guidelines for Submitting Report button to the right of the first bullet.

- If the report has no separate appendices or sub-reports, then push the Submit button. If you have appendices or sub-reports that should be associated with the main report, press the Add Volume button. This will submit the report and bring up a form for the new volume. Enter data on that volume and hit Submit.

- Once you have completed the process, please mail one double-sided bound paper copy of the report to:

California Energy Commission
Attn: Peter Puglia
Energy Specialist
California Energy Commission, 
Energy Efficiency and Demand Analysis Division
1516 9th Street, MS 22
Sacramento, CA 95814-5512

We thank you for taking the effort to keep the database up to date and relevant.